| World Trade Organization |  |
| --- | --- |
|  | G/VAL/17/Rev.1 8 December 1999 |
|  | (99-5395) |
| Committee on Customs Valuation | Original: Spanish |

reservation by paraguay under paragraph 1 of annex III of

the agreement on implementation of article vii of

the general agreement on tariffs and trade 1994

Decision

Revision

The following Decision concerning the reservation by Paraguay under paragraph 1 of Annex III of the Agreement on Customs Valuation was adopted by the Committee on 12 November 1999.

_______________

Taking into account the request by the Government of Paraguay under paragraph 1 of Annex III of the Agreement on Implementation of Article VII of the General Agreement on Tariffs and Trade 1994 (WTO Agreement on Customs Valuation), done at Marrakesh on 15 April 1994, for an extension of the period for the application of the provisions of the Agreement,

Recognizing that, on 1 January 1995, Paraguay became a contracting party of the WTO Agreement on Customs Valuation and, under paragraph 1 of Article 20 of the Agreement, requested an extension of five years as from 1 January 1995, the effective date of said Agreement, and is therefore scheduled to apply the rules of the aforementioned Agreement as from 1 January 2000,

Considering that Paraguay has made substantial endeavours to implement the provisions of the WTO Agreement on Customs Valuation,

Considering further that Paraguay has an ongoing interest in receiving technical assistance in support of the implementation and application of the WTO Agreement on Customs Valuation,

Noting Paraguay's commitment and endeavours to reform and modernize its customs administration,

Noting that the Paraguayan authorities have established a detailed work programme involving the respective ministries and offices in order to make it possible to draw up and approve its legislation as well as to adapt its legal and administrative procedures, including training, dissemination of information and other activities, in order to implement and apply the WTO Agreement on Customs Valuation,

Seeing as regards paragraph 2 of Annex III of the WTO Agreement on Customs Valuation, that Paraguay currently values goods on the basis of officially-established minimum values, solely in respect of the following products:

(a)	Worn clothing and other worn articles of tariff headings 63.09 and 63.10;

(b)	used footwear, of Chapter 64;  and

(c)	used vehicles other than railway or tramway rolling stock, and parts and accessories thereof, of Chapter 87.

Seeing also Paraguay's intention not to apply these minimum values to other products during the extension period requested for the implementation of the WTO Agreement on Customs Valuation, and to endeavour not to apply these minimum values to any other product upon expiry of the requested extension period,

Seeing that the Government of Paraguay is already applying paragraph 2 of the Decision on the Valuation of Carrier Media Bearing Software for Data Processing Equipment,

Seeing that the Government of Paraguay neither uses nor envisages using pre-inspection services for the purposes of customs administration and valuation,

Recognizing Paraguay's indication that this would be the only extension request for the implementation of the WTO Customs Valuation Agreement,

The Members, pursuant to the provisions of paragraph 1 of Annex III of the WTO Agreement on Customs Valuation,

Decide in the light of the exceptional circumstances mentioned above, that:

1.	Subject to the terms and conditions mentioned hereunder, Paraguay may postpone the implementation of the provisions of the WTO Agreement on Customs Valuation for a period not extending beyond 1 January 2001;

2.	The Government of Paraguay shall report to the Committee on Customs Valuation, at the Committee's regular meetings scheduled for the year 2000, on the progress made in executing the work programme contained in Annex II and on the level of implementation of the WTO Agreement on Customs Valuation, in keeping with the terms and conditions of this Decision;

3.	This Decision neither prejudges nor prejudices the rights and obligations of Paraguay under the WTO Agreements, in particular, rights and obligations under the WTO Agreement on Customs Valuation.

WORK PROGRAMME

Period 2000-2001

General Objective:  To strengthen the application of the Agreement on Implementation of Article VII of the GATT 1994 (Customs Valuation)

| SPECIFIC OBJECTIVES | ACTIVITIES | PERIOD | REQUIREMENTS | GOALS | INDICATORS |
| --- | --- | --- | --- | --- | --- |
| 1. To update the legal framework of the Customs Service | To adapt the Paraguayan Customs Code so as to meet the requirements of international trade and bring it into line with regional regulations and treaties signed by the country. To update its regulations by incorporating new regimes, destinations and customs figures. To incorporate into the regulations the legal recognition of the application of technology to the procedures. | 12 months | To recruit consultants with experience in drafting customs regulations and in processes of integration (4 months/consultancy). To provide the facilities to assist customs inspections at frontiers (vehicles, boats, infra-red equipment, etc.) | Updated framework of customs regulations To achieve effective customs control at frontiers. | 24 months: Draft Customs Code completed, revised and submitted; Draft Regulations completed, revised and submitted. Decrease in the percentage of estimated smuggling (increase in customs revenue). |
|  | To create the legal framework to regulate frontier inspections (air, land and river). |  |  |  |  |
| 2. To simplify customs procedures | Reorganization of procedures and customs documentation through the use of technology. | 12 months | To establish working groups of officials of the Paraguayan Customs Service. | All customs procedures to be automated. | To reduce clerical costs and time (user surveys). |
|  | To draft procedural manuals. |  | To carry out training courses on model customs procedures. | Implementation completed. |  |
|  | To draw up risk assessment programmes so as to improve selectivity in checking goods. |  | To make a survey of the procedures used in the most productive customs units. | Chemical laboratory installed and functioning. |  |
|  | To set up a laboratory to meet customs needs. |  | To hire consultants specializing in procedures (6 months) |  |  |
|  |  |  | To hire consultants to establish the laboratory and organize its structure (6 months) |  |  |
|  |  |  | To set up laboratory teams. |  |  |
| 3. To strengthen the Customs Valuation Service | To adapt the valuation system so as to fully comply with Article VII of the GATT. To strengthen the local units. To prepare a manual on customs valuation. To structure the Central Unit of the Valuation Service. To establish a technical library to provide consultation and support services. | 12 months | To hire computer experts specializing in valuation (3 months). To organize training in a country specializing in this field, 2 officials (1 week). To purchase 4 high-velocity scanning units. To speed up the establishment and operation of a database. | To fully apply the GATT concept of value. | To introduce in the next 12 months the application of the GATT concept of value and establish effective controls of the transaction value in a posteriori form of 30 per cent of the declarations made, using procedures that allow for the selection and effective control of sensitive products. |
| 4. To improve the auditing of customs administration | To improve auditing in the areas of internal and external control. To select, with a view to achieving greater efficiency and flexibility in the controls, a group of major importers. To establish units to analyse and process the information so as to make the auditing more efficient. To prepare risk assessment programmes so as to improve efficiency in the selection of "a posteriori" control. To define, develop and establish a database to facilitate inspections. To harmonize inspection procedures with the Sub-Secretariat of Taxation. | 12 months | To hire a specialized international consultant to reorganize the system of auditing (3 months). To hire consultants specialized in customs auditing to select and train the auditors (3 months). To purchase computer equipment (10 computers). | All users to be inspected. | Inspection in the first year of 50% of commercial agents. Inspection in the 2nd year of 100 per cent of commercial agents. |
| 5. To upgrade the SOFIA computer system | To develop programmes to process the conditional relief and special customs import regimes. To prepare the appropriate manuals. To extend the SOFIA system to the customs units that are not currently linked to it. To improve the training of customs officials in using the system. | 12 months | Recruitment of highly qualified computer staff. Training of a group of customs experts for optimization of computerized tariffs. To carry out specific training programmes in this field. | 100% utilization by the institution of the technology for inspection. | Management of customs declarations: should be processed 100% by administrations equipped with the SOFIA computer system. |
| 6. To establish a new organizational structure | To design and implement the organizational structure with job descriptions. | 8 months | Specialized consultants (4 months). | New structure designed and implemented so as to meet requirements. | Organizational structure able to provide efficient support to the new customs service. |
| 7. To make optimum use of the existing human resources and establish training programmes | To establish an administrative career structure with rules for recruitment, entry selection and promotion. To establish salary levels and incentives corresponding to the levels of responsibility. To determine areas of training, and carry out programmes. | 12 months | Consultants in human resources management (4 months). Support in providing infrastructure and teams for training. | To establish an administrative career structure. | Incorporation of professionals: 1st year 10%; 2nd year 25% |
| 8. To step up inspection so as to ensure verification of origin | To establish a specific unit with regard to origin. To prepare a manual on inspection procedures for the verification of origin. To strengthen links with other customs services that could lead to the establishment of risk parameters. To establish a database on the provenance and origin of goods. | 8 months |  | To provide the customs service with the expertise required in this field to fulfil the country's commitments. | Levels of efficiency in determining the origin of goods. |

__________

# Footnotes

See document G/VAL/M/12 to be issued.