| World Trade Organization |  |
| --- | --- |
|  | G/VAL/22 10 March 2000 |
|  | (00-0944) |
| Committee on Customs Valuation |  |

reservation by the dominican republic under paragraph 1 of

annex III of the agreement on implementation of article vii

of the general agreement on tariffs and trade 1994

Decision

The following Decision concerning the reservation by the Dominican Republic under paragraph 1 of Annex III of the Agreement on Customs Valuation was adopted by the Committee on 3 March 2000.

_______________

TAKING NOTE of the Government of the Dominican Republic's request under paragraph 1 of Annex III of the Agreement on Implementation of Article VII of the General Agreement on Tariffs and Trade 1994 ("WTO Agreement on Customs Valuation"), done at Marrakesh on 15 April 1994, to extend its delay in the application of the provisions of that Agreement;

RECOGNIZING that on 9 March 1995, the Dominican Republic became a contracting party to the WTO Agreement on Customs Valuation and invoked paragraph 1 of Article 20 of that Agreement to delay application of its provisions for a period of five years from the date of entry into force of the Agreement on 9 March 1995, and was therefore scheduled to apply the provisions of that Agreement by 9 March 2000;

CONSIDERING the Dominican Republic has made substantial efforts to implement the provisions of the WTO Agreement on Customs Valuation;

CONSIDERING also that the Dominican Republic has received technical assistance and has a continuing interest in taking advantage of technical assistance in support of implementation and application of the WTO Agreement on Customs Valuation;

NOTING the Dominican Republic's long-standing commitment and considerable efforts in reforming and modernizing its customs administration;

NOTING also the Dominican Republic's objective of ensuring the effective implementation and administration of the WTO Agreement on Customs Valuation;

NOTING that the Dominican Republic's authorities have established a detailed work programme, involving the relevant ministries and agency, to enable the elaboration and approval of its legislation and the completion of its domestic administrative and legal procedures, including training, dissemination of information, and other actions, for implementing and applying the WTO Agreement on Customs Valuation;

NOTING that, in regard of paragraph 2 of Annex III of the WTO Agreement on Customs Valuation, the Dominican Republic will not apply minimum values to any products when it implements the WTO Agreement on Customs Valuation after the expiration of this requested period of delay in its implementation;

NOTING that the Dominican Republic already applies paragraph 2 of the Decision on the Valuation of Carrier Media Bearing Software for Data Processing Equipment;

NOTING that the Government of the Dominican Republic does not use or plan to use preshipment inspection services for purposes of customs valuation;

RECOGNIZING the Dominican Republic's indication that this would be a single request for an extension to delay its implementation of the WTO Agreement on Customs Valuation;

Members, acting pursuant to the provisions of paragraph 1 of Annex III of the WTO Agreement on Customs Valuation,

DECIDE, in view of the exceptional circumstances set out above, that:

1.	Subject to the terms and conditions set out hereunder, the Dominican Republic may delay further the application of the provisions of the WTO Agreement on Customs Valuation for a period not extending beyond 1 July 2001.

2.	The Government of the Dominican Republic shall report to the Committee on Customs Valuation by 30 September 2000 and again by 28 February 2001 on the progress in fulfilling the work programme in Attachment I and the status of its implementation of the WTO Agreement on Customs Valuation under the terms and conditions of this Decision.

3.	This Decision shall not prejudice the rights and obligations of the Dominican Republic under the WTO Agreements, in particular those rights and obligations under the WTO Agreement on Customs Valuation.

DOMINICAN REPUBLIC

GENERAL CUSTOMS DIRECTORATE (DGA)

Work Programme

Period 2000 - 2002

General objective:	Completion of the process of implementation of the Customs Valuation Agreement

(Implementation of Article VII of the GATT 1994)

| Specific objectives | Activities | Period | Requirements | Goals | Indicators |
| --- | --- | --- | --- | --- | --- |
| 1. Updating of the legal structure of the Dominican customs | (a) Approval of the Draft Tariff Reform and development of legislation to ensure its efficient implementation. (b) Approval of the Draft Customs Law in order to bring the institution into conformity with modern trade requirements and with the commitments assumed. (c) Updating of the regulations necessary for the implementation of the new legal system. | 18 months | Consultations with the economic sectors in order to achieve the broadest possible agreement on the implementation of the New Tariff Code and the Dominican Customs Law. | New Tariff Code and Customs Law | 24 months: full entry into force of the Customs Code and the Dominican Customs Law with the corresponding regulations for their implementation in all customs areas. |
| 2. Simplification of customs procedures | (a) Completion of the General Manual of Procedures for all operational and technical areas. (b) Completion of the process of amending all of the documents used for internal control. (c) Development of risk assessment programmes to enhance selectivity in the inspection of goods. | 18 months | Technical assistance of international bodies for reviewing the outcome of the process of re-engineering procedures and amending documents. Intensification of work towards achieving conformity of all customs officials directly involved in the application of the entire internal reform process. | Automation of all customs procedures. Monitoring of the reformed customs structure. Installation of new laboratory equipment. | 18 months: reduction to a minimum of the time required for clearing goods through customs and of the costs of that process. |
| 3. Strengthening of the customs valuation service | (a) Completion of the adaptation of the valuation system to bring it into full conformity with Article VII of the GATT 1994. (b) Development of valuation regulations so as to fully incorporate these provisions into the internal operating system. (c) Strengthening of the central valuation unit in the DGA. (d) Strengthening of the local units responsible for operating in accordance with the new WTO valuation system. | 15 months | Hiring of specialists in the implementation of WTO valuation systems using electronic tools (eight months). Organization of specialized training for six officials over a period of four weeks in countries with experience in implementing the new valuation system. Completion of the database organized in the valuation department of the DGA. | Full application of the GATT 1994 Customs Valuation Agreement. | 15 months: application of the GATT valuation concept and maintenance of effective control of the transaction value of 50% of declarations using mechanisms that permit the selection and control of sensitive goods. |
| 4. Improve the auditing of customs administration | (a) Improvement of the auditing department in the areas of internal and external control. (b) Selection of a representative sample of major importers to confirm the efficiency and flexibility of controls. (c) Development of risk assessment programmes in order to make the subsequent control section more effective. (d) Placing auditing functions under the Technical Sub-Directorate of the DGA. | 18 months | Hiring of an international consultant specialized in the organization of auditing functions (six months). Advanced training programme for auditors (six months). Purchase of new computer equipment with high storage capacity. | All customs service users. | 12 months: scope of inspection in one year, up to 50% of service users. 18 months: scope of inspection in the second year up to 90% of service users. |
| 5. Upgrading of the computer system | (a) Expansion of programmes for the conditional relief and special customs import regimes. (b) Preparation of manuals containing the operational design of the network. (c) Expansion of the computer system to all points of the network. (d) Further application of the continued training programme to improve the management of the computer system by authorized officials. | 15 months | Training of highly qualified professionals in data processing. Formation of technical customs teams to optimize computerized tariffs. Further implementation of the special continued training programme in the area of network control and operation. | Complete utilization of computer resources for the control of the new valuation system. | In 15 months: all customs declarations should be processed by computer. |
| 6. Stepping up the process of upgrading the organizational structure | (a) Completion of the development of the organizational structure with job descriptions and definition of administrative and technical functions. (b) Definition of the administrative career structure with rules governing recruitment, entry selection and promotion. (c) Determination of areas requiring training and implementation of the corresponding programmes. | 18 months | Specialized consultation with domestic companies. | Introduction of the new structure. | In 12 months: establishment of a new structure in keeping with the requirements of a modern customs administration. |

__________

# Footnotes

See document G/VAL/M/13 to be issued.

Attachment 1 – Work Programme.

G/VAL/5.