| World Trade Organization | RESTRICTED |
| --- | --- |
|  | G/VAL/W/84 12 June 2001 |
|  | (01-2905) |
| Committee on Customs Valuation | Original: French |

communication from rwanda concerning paragraph 1 of

annex iii of the agreement on implementation

of article vii of the general agreement

on tariffs and trade 1994

The following communication, dated 21 May 2001, has been received from the Ministry of Commerce, Industry and Tourism of the Republic of Rwanda.

_______________

When our country became a Member of the World Trade Organization (WTO), we requested and were granted deferral of application of the above Agreement for a period of five years.  The deadline expires on 22 May 2001.

In view of our country's special circumstances and the scant resources at our disposal, we have been unable to take all the requisite steps for implementation within the prescribed time limit.

In our letter No. 0847/15/04.1/2000 of 31 May 2000, we accordingly asked you to consider the possibility of postponing the date of application of the Agreement for a further three years, as from 22 May 2001, pursuant to the provisions of Annex III, paragraph 1, of the Agreement.

This additional period will enable us – with technical support from the WTO, the World Customs Organization (WCO) and any Members willing, by virtue of Article 20.3 of the Agreement, to assist us in our efforts – to introduce all the reforms needed to give effect to this accord.

You will find a draft plan of action enclosed for your information. Its implementation will depend largely on the amount of technical assistance that may be given to us.

We are convinced that we can, as always, count on your understanding and trust that our request will receive favourable consideration.

Plan of action for implementation of the WTO Agreement

Five prerequisites will need to be met before the GATT valuation system can be applied:

- Revise customs legislation;

- computerize customs offices;

- restructure the Department;

- train customs staff;

- train the private sector.

- Revision of customs legislation

- Objective:

-	To revise and harmonize customs legislation in the light of the Kyoto Convention, the GATT Agreement and the Law Establishing the Rwanda Revenue Authority.

- Achievements and future work (see table below)

| Activities | Achievements | Needs for technical assistance | Timeframe | Comments |
| --- | --- | --- | --- | --- |
| Creation of the Commission on the revision of customs legislation | - | - | - | Created on 20/01/2000 |
| Harmonization of customs legislation with the revised Kyoto Convention | - | WCO training seminar on the Kyoto Convention held from 5-8/12/2000 | 1 week | 3 members of the Commission took part in the seminar |
| Comparative analysis of the Kyoto Convention and customs legislation | Work began on 27 January 2000 and was completed in January 2001 | - | 12 months | Completed |
| Finalization of a technical opinion on the Kyoto Convention | - | - | 10 May | Completed |
| First examination of the technical opinion by the Commission | - | - | 15 May 2001 | Completed |
| Second examination of the technical opinion by the Commission | - | - | 17 May 2001 | - |
| Transmission of the technical opinion to the CG | - | - | 18 May 2001 | It is recommended that the draft be submitted to the WCO for analysis before reaching any decision |
| Identification of the provisions of the GATT Agreement to be incorporated in customs legislation | - | - | 31 May 2001 | Distribution of tasks |
| Evaluation of revision work | - | - | 30 August 2001 | - |
| Completion of revision work | - | - | 20 November 2001 | - |
| Examination of the draft law by a WCO expert | - | Expert from the WCO Valuation Directorate | 20 December 2001 | It is recommended that the draft law be submitted to the WCO prior to its examination by the decision-makers |
| Presentation of the draft law to the CG | - | - | 28 December 2001 | - |
| Submission of the draft law to the Minister of Finance and Economic Planning | - | - | 25 January 2002 | - |

- Computerization of customs offices

- Objectives:

-	Purchase computer equipment;

-	develop programmes for the automatic registration and processing of customs declarations ("DMCs") on the basis of file data (importer, supplier, goods);

-	investigate options for automatically calculating the value to be declared (IT techniques);

-	extend the ASYCUDA programme to border posts;

-	prepare the necessary user's manuals.

- Achievements and future work (see table below)

| Activities | Achievements | Needs for technical assistance | Timeframe | Comments |
| --- | --- | --- | --- | --- |
| Purchase of computer equipment | - Gikondo and the Airport are already equipped and operational - The second stage should focus on major offices (Gatuna, Butare, etc.) | - Equipment - Staff training | May 2001 | Electrification is necessary before border posts can be equipped, as most of them do not have electricity |
| Development of programmes for automatic registration and processing of customs declarations ("DMCs") | - Gikondo and the Airport are already using UNIX software - A vast amount of data is available in ASYCUDA | Guidance from the WCO and UNCTAD to determine whether the UNIX/ASYCUDA software is compatible with the GATT valuation system | May 2002 | Request for technical assistance recently submitted to the WCO |
| Investigation of options for automatically calculating the value to be declared | - | Guidance from the WTO or UNCTAD as to how this is done in countries already applying the GATT Agreement | August 2001 | The RRA should consider study tours to gain experience from countries already applying the system |
| Extension of ASYCUDA to border posts | Proposal to introduce the transit module in offices facing an extremely heavy workload | Support, in the form of funding or equipment, from the WCO, UNCTAD, the WTO or COMESA | January 2002 | Such an extension is advisable as it will facilitate the exchange of information between border posts and the Directorate-General |
| Preparation of user's manuals for computer programmes | - | IT expert | Before March 2002 | This will, however, depend on the programmes selected |
| Staff training | - | IT expert | Before March 2002 | - Priority given to officers of the Customs Valuation Section and inspectors required to apply the system - Recruitment and training of a national expert |

- Restructuring of the Department

- Objectives:

-	Reorganize the Valuation Division;

-	strengthen the verification process;

-	create a rules of origin section;

-	create a post-clearance control section.

- Achievements and future work (see table below)

| Activities | Achievements | Needs for technical assistance | Timeframe | Comments |
| --- | --- | --- | --- | --- |
| Reorganization of the Valuation Division | 2 existing sections: - Tariff Section - Customs Valuation Section | Meeting held with a KPMG expert | April 2001 | - Definition of new responsibilities - Creation of the Rules of Origin Section |
| Strengthening of the verification process through the appointment of two officers in charge of risk management and data collection at Gikondo and the Airport | - | - | June 2001 | - |
| Establishment of a database on the provenance and origin of goods Drafting of a manual on how to monitor respect for rules of origin | - | - | Before March 2002 Before March 2002 | - |

- Staff training

- Objectives:

-	Target customs officers requiring training as a matter of priority;

-	propose a timetable and specify the purpose of training.

- Achievements and future work (see table below)

| Activities | Achievements | Needs for technical assistance | Timeframe | Comments |
| --- | --- | --- | --- | --- |
| Training of members of the GATT Commission | 2 WCO seminars on the GATT valuation system organized in Kigali in: - March 2000 - April 2001 | WCO | 1 week | Study tours should be arranged to supplement such training |
| Training of customs personnel | New customs legislation | National instructor | 2 weeks | - |
| Training of examiners + officers of the Customs Valuation Section | Enforcement course | WCO/WTO | 1 month | Training expert or fellowship programme |
| Training of inspectors + officers of the Customs Valuation Section | Means and methods of ensuring post-clearance control | WCO/WTO | 1 month | Training expert or fellowship programme |
| Training of officers of the Rules of Origin Section | Rules of origin | WCO/WTO | 1 month | Training expert or fellowship programme |
| Training on the WTO Agreement for private-sector representatives | - | National instructor or expert from the International Chamber of Commerce | 2 weeks | Request WTO assistance |

__________